## PMR SIGNED
|  | ANNEX A | [18 empty] | ANNEX B- INFRASTRUCTURE PROJECT
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | CITY GOVERNMENT OF SORSOGON Procurement Monitoring Report as of JUNE 17, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
CW 2020-011-056 | CONSTRUCTION OF SMALL DWELLING UNITS, RELOCATION SITE, SPPVS BIBINCAHAN | [19 empty] | CMO | NO | Competitive Bidding | N/A | 2020-02-12 | 2020-09-12 | 2021-01-03 | 2021-01-03 | 2021-02-03 | 2021-04-03 | 2021-10-03 | 2021-11-03 | 2021-12-03 | 3/15/201 | 75 cal days | suspended | GoP | 4996816.75 |  | 4996816.75 | 4959752.59 |  | 4959752.59 | PICE/COA | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-12 | RGE CONSTRUCTION AND SUPPLY
CW 2021-02-004 | CONSTRUCTION/REHABILITATION OF ROAD NETWORK@ GUINLAJON WEST | [19 empty] | CMO | NO | Competitive Bidding | N/A | 2021-11-02 | 2/18/2021 | 3/03/201 | 2021-03-03 | 2021-05-03 | 2021-09-03 | 2021-10-03 | 2021-11-03 | 2021-12-03 | 3/15/201 | 50 cal days | 2021-07-05 | GoP | 3955225.48 |  | 3955225.48 | 3930198.18 |  | 3930198.18 | PICE/COA | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 | PILANG 28 CONSTRUCTION INCORPORATED
CW 2021-02-005 | REHABILITATION & EXTENSION OF RIVER CONTROL @ BALETE, BACON DIST | [19 empty] | CDRRMO | NO | Competitive Bidding | 1/20/2021 | 2/19/2021 | 2/26/2021 | 3/15/2021 | 3/15/2021 | 3/16/2021 | 3/23/2021 | 3/24/2021 | 3/25/2021 | 3/29/2021 | 3/31/2021 | 230 cal days | 10/21/2021 | GoP | 15099960.12 |  | 15099960.12 | 15066546.11 |  | 15066546.11 | PICE/COA | 2/19/2021 | 2/19/2021 | 2/19/2021 | 2/19/2021 | 2/19/2021 | 2/19/2021 | KRATOS DEVELOPMENT CORPORATION
CW 2021-03-006 | CONSTRUCTION OF MARKET STALLS @ POBLACION, BACON DIST | [19 empty] | CEO | NO | Competitive Bidding | N/A | 2021-04-03 | 2021-12-03 | 3/25/2021 | 3/25/2021 | 3/26/2021 | 3/29/2021 | 3/30/2021 | 2021-05-04 | 2021-06-04 | 2021-07-04 | 180 cal days | 10/18/2021 | GoP | 4999999.9 |  | 4999999.9 | 4944371.42 |  | 4944371.42 | PICE/COA | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | RMH CONSTRUCTION AND SUPPLY
CW 2021-03-008 | UPGRADING AND REPAIR OF IRRIGATION STRUCTURE | [19 empty] | CDRRMO | NO | Competitive Bidding | N/A | 2021-04-03 | 2021-12-03 | 3/25/2021 | 3/25/2021 | 3/26/2021 | 3/29/2021 | 3/30/2021 | 2021-05-04 | 2021-06-04 | 2021-07-04 | 90 cal days | 7/19/2021 | GoP | 3000000 |  | 3000000 | 2975097.5 |  | 2975097.5 | PICE/COA | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | 2021-04-03 | CHEREEL CONSTRUCTION AND SUPPLY
CW 2021-04-010 | CONST. OF PERIMETER FENCE AT CITY NURSERY BBINCAHAN | [19 empty] | CITY AGRICULTURE | NO | Competitive Bidding | N/A | 4/23/2021 | 2021-03-05 | 5/17/2021 | 5/17/2021 | 5/18/2021 | 5/20/2021 | 5/26/2021 | 5/27/2021 | 5/28/2021 | 5/31/2021 | 90 cal days | 2021-10-09 | GoP | 2029179.21 |  | 2029179.21 | 1989179.41 |  | 1989179.41 | PICE/COA | 4/26/2021 | 4/26/2021 | 4/26/2021 | 4/26/2021 | 4/26/2021 | 4/26/2021 | ALHADRAX CONSTRUCTION AND SUPPLY
CW 2021-04-011 | PROPOSED LEVEL III BARANGAY MARINAS WATER SUPPLY SYSTEM | [19 empty] | CMO | NO | Competitive Bidding | N/A | 4/26/2021 | 2021-03-05 | 5/17/2021 | 5/17/2021 | 5/19/2021 | 5/25/2021 | 5/26/2021 | 5/27/2021 | 5/28/2021 | 5/31/2021 | 120 cal days | 9/13/2021 | GoP | 4703223 |  | 4703223 | 4688699.17 |  | 4688699.17 | PICE/COA | 4/26/2021 | 4/26/2021 | 4/26/2021 | 4/26/2021 | 4/26/2021 | 4/26/2021 | KRATOS DEVELOPMENT CORPORATION
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 38784404.46
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 38553844.38
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 230560.08
0N-GOING PROCUREMENT ACTIVITIES
0
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 0
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | NANCY D. CABALLERO | [10 empty] | DR. ROLANDO E. DEALCA | [10 empty] | MA. ESTER E. HAMOR
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement