## Trust Fund Utilization
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd Quarter, C.Y. 2022
CITY OF SORSOGON
PROGRAM OR TARGET | LOCATION | TOTAL FUNDS AVAILABLE (COST) | DATE STARTED (RECEIPT) | TARGET DATE OF COMPLETION | PROJECT STATUS |  | NO. OF EXTENSIONS, IF ANY | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DAR 1st Tranche Multipurpose for SMBO | Sorsogon City | 184000 | 2018-11-01 |  | 84% | 153689.5 |  | Construction in Progress
LGSF - Assistance to Cities: Proposed Construction of Sorsogon City Eco-Park | Sorsogon City | 20898428 | 2021-06-01 |  |  |  |  | Not Yet Implemented
Department of Agriculture (Agriculture Training Institute RTC -V) Livestock National (1st Tranche Establishment of Swine Multiplier and Techno Demo Farm) | Sorsogon City | 3000000 | 2021-05-01 |  | 65% | 3238358.16 | with LGU counterpart | on going
Department of Agriculture (Agriculture Training Institute RTC -V) Livestock National (2nd Tranche Establishment of Swine Multiplier and Techno Demo Farm) | Sorsogon City | 2000000 | 2021-09-01
Department of Agriculture (Agriculture Training Institute RTC-V): Livestock National (Implementation of Swine Multiplier Farm | Sorsogon City | 1500000 | 2022-03-01
Department of Agriculture (Agriculture Training Institute RTC-V): 1st Tranche Implementation of enhanced KADIWA Ani at Kita | Sorsogon City | 450000 | 2021-09-01 |  | 45.05% | 2971566.31 | with LGU counterpart | Construction in Progress
Department of Health: One Covid-19 Allowance (Jan. 2022) | Sorsogon City | 1660500 | 2022-06-01 |  |  |  |  | on going
Department of Labor and Employment ROV: TUPAD Wages & PPEs for LGU- Sorsogon City (278 beneficiaries) | Sorsogon City | 931300 | 2021-10-01 |  | 7% | 66750 |  | on going
DOE: BACMAN Geothermal DLF - relief assistance due to COVID 19 | Sorsogon City | 3771960.37 | Jan-Dec. 2020 |  | 84% | 3751867.6 |  | On-going
|  | 107993.05 | 2021-02-01
|  | 124092.8 | 2021-05-01
|  | 255663.1 | 2021-10-01
|  | 124149.96 | 2022-03-01
|  | 98036.76 | 2022-04-01
DOE: BACMAN Geothermal RWMHEEF - relief assistance due to COVID 19 | Sorsogon City | 6160822.88 | Jan-Dec. 2020 |  | 57% | 3889749.08 |  | On-going
|  | 107993.05 | 2021-02-01
|  | 124092.8 | 2021-05-01
|  | 255663.1 | 2021-10-01
|  | 124149.96 | 2022-03-01
|  | 98036.76 | 2022-04-01
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness
of the data or information contained in this document.
(Sgd) JINKY F. AQUINO |  | (Sgd) CHRISTINE N. MERALPES |  |  |  | (Sgd) MA. ESTER E. HAMOR
City Budget Officer |  | City Accountant |  |  |  | City Mayor